## Test Cases
TC ID | Bug ID | Module | Test Case Title | Test Steps | Expected Result | Priority | Status | Actual Result | Remarks
TC-001 | BUG-001 | Frontend | Verify only one description is displayed in the Option Description section | 1. Navigate to the screen containing the Option Description section. 2. Select an option. 3. Observe the description(s) displayed. | Only a single description is shown in the Option Description section; no duplicate descriptions appear. | Medium | Failed | Multiple descriptions are still displayed in the Option Description section. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-002 | BUG-002 | Frontend | Verify "PocketO" text is correctly changed to "PocketTO" | 1. Navigate through the app screens where the app name/branding text appears. 2. Check the text for "PocketO" vs "PocketTO". | All instances correctly display "PocketTO" instead of "PocketO". | Low | Failed | Text still shows "PocketO" instead of "PocketTO" in some/all locations. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-003 | BUG-003 | Frontend | Verify Pull-to-Refresh functionality works on the Home screen | 1. Navigate to the Home screen. 2. Perform a pull-down gesture from the top of the screen. 3. Observe the screen's behaviour. | Home screen refreshes its content correctly in response to the pull-to-refresh gesture. | Medium | Failed | Pull-to-Refresh functionality is still not available on the Home screen. | Bug still marked "Open" in bug report — retest once fix is deployed.
TC-004 | BUG-004 | Frontend | Verify the button text remains enabled/visible even when no option is selected | 1. Navigate to the relevant screen with the selectable options and button. 2. Do not select any option. 3. Check the state and text of the button. | Button text remains enabled/visible even when no option has been selected. | Low | Passed | Button text remains enabled/visible even when no option has been selected. | Fix verified as per bug report status (Done).
TC-005 | BUG-005 | Frontend | Verify the Description text field height is increased | 1. Navigate to the screen containing the Description text field. 2. Check the field's height against the previous/updated design. | Description text field displays with increased height, matching the updated design. | Low | Passed | Description text field displays with increased height, matching the updated design. | Fix verified as per bug report status (Done).
TC-006 | BUG-006 | Frontend | Verify the PocketTO link and its arrow button are removed and no longer log the user out | 1. Navigate to the screen that previously contained the PocketTO link and arrow button. 2. Check whether the link and arrow button are present. 3. If any remnant exists, click it and observe the outcome. | PocketTO link and its arrow button are fully removed from the screen; no action logs the user out. | Medium | Passed | PocketTO link and its arrow button are fully removed from the screen; no action logs the user out. | Fix verified as per bug report status (Done).
TC-007 | BUG-007 | Frontend | Verify the CrewLink logo is removed when the app is minimized | 1. Open the app. 2. Minimize the app (send to background). 3. Check for the CrewLink logo (e.g. in a splash/recents view). | CrewLink logo is not displayed when the app is minimized. | Low | Passed | CrewLink logo is not displayed when the app is minimized. | Fix verified as per bug report status (Done).

## Summary
PocketTO - Test Case Summary
Total Bugs Covered | 7
Total Test Cases | 7
Frontend Module Bugs | 7
Backend Module Bugs | 0
High Priority | 0
Medium Priority | 3
Low Priority | 4
Passed | 4
Failed | 3